## Sheet1
Date: | Goals : | Completed: | What did not work: | What worked:
2018-11-11 | Create database | Databse | Databse took longer than expected to connect | Switched to gitHub Desktop
| Connect database | Connected Database | Attempted git hub command line and it sucked | Meeting in person improved communication
| create login page | Created basic login page
Create Registration page
2018-11-18 | Create password hash for login | Created password hash | Communication: Mike and Zack Spent 1.5 hours doing the same thing | Set aside more time to work on project so we comleted more
| Create Registration page | Created registration page
| Connect registration page to database | Connected registration page to database
| test registration info to database | tested registration page
2018-11-23 | Refactor and Test code for bugs | We cleaned up the login and registration page | Had to improve how we communicated who was working on what | We started having a quick meeting before each session and wrote on the white board who was doing what to avoid github problems
|  | got rid of duplicate code or code that we used to test simple stuff | Our decision to create our HTML pages from scratch means that our developers will have a good understanding of the page structure, but progress is slower than it would be with a premade online template.
2018-11-25 | Develop classes for SugarDaddy, Cougar, GoldDigger Female, and GoldDigger male | Created Classes for SugarDaddy, Cougar, GoldDigger Female, and GoldDigger male | Using the this-> identifier was confusing | Mike is a stud
| Create class functions | Created getters and setters | Learning the syntax of functions in PHP took longer than expected | Brian is a stud
|  | Wrote the Constructor | Learning inheiritance and polymorphism in PHP was confusing at first | Zack is a stud
Thanks to CIS 210 we understood polymorphism so the syntax was the only issue
2018-12-02 | Zip-Code API integration | Zip-Code API | API key ended up changing every 24 hours | We met at 9am so we had all day to work on the project
| Create algorithm for matching | Created algorithm for matching | Had trouble accessing the class structure
| Streamlined website flow | Made the website flow better | getting functions to work was rough
| Refactor code | Deleted code we ended up not needing
| add comments | added comments to php and html to help us read the code better
2018-12-03 | Output matches to current user | Output the matches | Misscommunication with gitHub Desktop led to us spending thirty minutes figuring out why we couldn’t push something | Once we figured out the gitHub desktop problem we were able to work on the same thing at the same time
| If the user wants to see next matches they click "new matches" and see next three matches | Completed next matches button and functionality | Could not get API to update on its own | Registered website so it updates itself for two weeks
Fix API so that the website fetches the newest API key